## Overview
Programme update
SAMPLE-FITOUT · data date 30 Jun 2024 · Whole programme
If these figures are struck through, or do not follow what is typed, Excel is calculating manually: press F9 to update them, or turn it on for good with Formulas › Calculation Options › Automatic.
| PERSON ▾ |  | SHOW ▾ |  | FIND
| Everyone |  | All activities | [5 empty] | Pick from the arrows - the figures and the lists below follow.
| ACTIVITIES |  | UPDATED | NEED ATTENTION |  | FINISHING LATE |  |  | CRITICAL |  |  | COMPLETE |  |  | UPDATES IN
| 60 |  | 0 | 3 |  | 0 |  |  | 15 |  |  | 33 |  |  | 0%
| Whole programme |  | of 60 have an entry | a cause, a date or a check missing |  | not finished, past the planned finish |  |  | not finished |  |  | actual finish entered |  |  | of the activities chosen
Updates by person |  |  | Click a name to open their sheet
| Responsible Person | Activities | Updates in | Need attention | Late | Critical | Complete | Return | [8 empty] | Updated | Not yet
| Dan Lowe - Design Lead | 19 | 0% | 0 | 0 | 0 | 19 | Waiting | [8 empty] | 0 | 19
| Priya Menon - Project Manager | 2 | 0% | 0 | 0 | 0 | 1 | Waiting | [8 empty] | 0 | 2
| Sara Moss - Site Manager | 20 | 0% | 2 | 0 | 7 | 6 | Waiting | [8 empty] | 0 | 20
| Tom Reid - Package Manager | 19 | 0% | 1 | 0 | 8 | 7 | Waiting | [8 empty] | 0 | 19
| Everyone | 60 | 0% | 3 | 0 | 15 | 33 | 0 of 60 | [8 empty] | 0
Activities · everyone · all activities | [15 empty] | Showing 60 of 60
| Person | Activity ID | Activity name | WBS | Status | Start | Finish | Physical % | Actual start | Actual finish | Actual % | Expected finish | Days late | Check | Delay cause | Notes
✎ | Dan Lowe - Design Lead | A1010 | Design package 01 | Engineering | Completed | 2024-01-05 | 2024-01-16 | 100 | 2024-01-05 | 2024-01-16 |  |  | 0 | ✓ Complete |  |  | 0 | 1
✎ | Dan Lowe - Design Lead | A1020 | Design package 02 | Engineering | Completed | 2024-01-10 | 2024-01-13 | 100 | 2024-01-10 | 2024-01-13 |  |  | 0 | ✓ Complete |  |  | 0 | 2
✎ | Dan Lowe - Design Lead | A1030 | Design package 03 | Engineering | Completed | 2024-01-11 | 2024-01-18 | 100 | 2024-01-11 | 2024-01-18 |  |  | 0 | ✓ Complete |  |  | 0 | 3
✎ | Dan Lowe - Design Lead | A1040 | Design package 04 | Engineering | Completed | 2024-01-14 | 2024-01-28 | 100 | 2024-01-14 | 2024-01-28 |  |  | 0 | ✓ Complete |  |  | 0 | 4
✎ | Dan Lowe - Design Lead | A1050 | Design package 05 | Engineering | Completed | 2024-01-21 | 2024-01-24 | 100 | 2024-01-21 | 2024-01-24 |  |  | 0 | ✓ Complete |  |  | 0 | 5
✎ | Dan Lowe - Design Lead | A1060 | Design package 06 | Engineering | Completed | 2024-01-22 | 2024-02-02 | 100 | 2024-01-22 | 2024-02-02 |  |  | 0 | ✓ Complete |  |  | 0 | 6
✎ | Dan Lowe - Design Lead | A1070 | Design package 07 | Engineering | Completed | 2024-01-27 | 2024-01-30 | 100 | 2024-01-27 | 2024-01-30 |  |  | 0 | ✓ Complete |  |  | 0 | 7
✎ | Dan Lowe - Design Lead | A1080 | Design package 08 | Engineering | Completed | 2024-01-28 | 2024-01-31 | 100 | 2024-01-28 | 2024-01-31 |  |  | 0 | ✓ Complete |  |  | 0 | 8
✎ | Dan Lowe - Design Lead | A1090 | Design package 09 | Engineering | Completed | 2024-01-29 | 2024-02-01 | 100 | 2024-01-29 | 2024-02-01 |  |  | 0 | ✓ Complete |  |  | 0 | 9
✎ | Dan Lowe - Design Lead | A1100 | Design package 10 | Engineering | Completed | 2024-01-30 | 2024-02-03 | 100 | 2024-01-30 | 2024-02-03 |  |  | 0 | ✓ Complete |  |  | 0 | 10
✎ | Dan Lowe - Design Lead | A1110 | Design package 11 | Engineering | Completed | 2024-02-01 | 2024-02-15 | 100 | 2024-02-01 | 2024-02-15 |  |  | 0 | ✓ Complete |  |  | 0 | 11
✎ | Dan Lowe - Design Lead | A1120 | Design package 12 | Engineering | Completed | 2024-02-08 | 2024-02-11 | 100 | 2024-02-08 | 2024-02-11 |  |  | 0 | ✓ Complete |  |  | 0 | 12
✎ | Dan Lowe - Design Lead | A1130 | Design package 13 | Engineering | Completed | 2024-02-09 | 2024-02-12 | 100 | 2024-02-09 | 2024-02-12 |  |  | 0 | ✓ Complete |  |  | 0 | 13
✎ | Dan Lowe - Design Lead | A1140 | Design package 14 | Engineering | Completed | 2024-02-10 | 2024-02-17 | 100 | 2024-02-10 | 2024-02-17 |  |  | 0 | ✓ Complete |  |  | 0 | 14
✎ | Dan Lowe - Design Lead | A1150 | Design package 15 | Engineering | Completed | 2024-02-13 | 2024-02-17 | 100 | 2024-02-13 | 2024-02-17 |  |  | 0 | ✓ Complete |  |  | 0 | 15
✎ | Dan Lowe - Design Lead | A1160 | Design package 16 | Engineering | Completed | 2024-02-15 | 2024-02-29 | 100 | 2024-02-15 | 2024-02-29 |  |  | 0 | ✓ Complete |  |  | 0 | 16
✎ | Dan Lowe - Design Lead | A1170 | Design package 17 | Engineering | Completed | 2024-02-22 | 2024-03-07 | 100 | 2024-02-22 | 2024-03-07 |  |  | 0 | ✓ Complete |  |  | 0 | 17
✎ | Dan Lowe - Design Lead | A1180 | Design package 18 | Engineering | Completed | 2024-02-29 | 2024-03-03 | 100 | 2024-02-29 | 2024-03-03 |  |  | 0 | ✓ Complete |  |  | 0 | 18
✎ | Dan Lowe - Design Lead | A1190 | Design package 19 | Engineering | Completed | 2024-03-01 | 2024-03-08 | 100 | 2024-03-01 | 2024-03-08 |  |  | 0 | ✓ Complete |  |  | 0 | 19
✎ | Priya Menon - Project Manager | A1000 | Design package 00 | Engineering | Completed | 2024-01-02 | 2024-01-09 | 100 | 2024-01-02 | 2024-01-09 |  |  | 0 | ✓ Complete |  |  | 0 | 20
✎ | Priya Menon - Project Manager | A1590 | Build package 59 | Construction | Not Started | 2025-01-03 | 2025-01-24 | 0 |  |  |  |  | 0 | Not changed yet |  |  | 0 | 21
✎ | Sara Moss - Site Manager | A1200 | Build package 20 | Construction | Completed | 2024-03-04 | 2024-03-18 | 100 | 2024-03-04 | 2024-03-18 |  |  | 0 | ✓ Complete |  |  | 0 | 22
✎ | Sara Moss - Site Manager | A1220 | Build package 22 | Construction | Completed | 2024-03-18 | 2024-04-01 | 100 | 2024-03-18 | 2024-04-01 |  |  | 0 | ✓ Complete |  |  | 0 | 23
✎ | Sara Moss - Site Manager | A1240 | Build package 24 | Construction | Completed | 2024-03-30 | 2024-06-08 | 100 | 2024-03-30 | 2024-06-08 |  |  | 0 | ✓ Complete |  |  | 0 | 24
✎ | Sara Moss - Site Manager | A1260 | Build package 26 | Construction | Completed | 2024-05-09 | 2024-05-16 | 100 | 2024-05-09 | 2024-05-16 |  |  | 0 | ✓ Complete |  |  | 0 | 25
✎ | Sara Moss - Site Manager | A1280 | Build package 28 | Construction | Completed | 2024-05-14 | 2024-06-04 | 100 | 2024-05-14 | 2024-06-04 |  |  | 0 | ✓ Complete |  |  | 0 | 26
✎ | Sara Moss - Site Manager | A1300 | Build package 30 | Construction | Completed | 2024-05-25 | 2024-06-08 | 100 | 2024-05-25 | 2024-06-08 |  |  | 0 | ✓ Complete |  |  | 0 | 27
✎ | Sara Moss - Site Manager | A1320 | Build package 32 | Construction | In Progress | 2024-06-04 | 2024-06-11 | 80 | 2024-06-04 |  |  |  | 0 | Finish date needed |  |  | 0 | 28
✎ | Sara Moss - Site Manager | A1340 | Build package 34 | Construction | In Progress | 2024-06-08 | 2024-06-12 | 40 | 2024-06-08 |  |  |  | 0 | Finish date needed |  |  | 0 | 29
✎ | Sara Moss - Site Manager | A1360 | Build package 36 | Construction | In Progress | 2024-06-15 | 2024-07-06 | 10 | 2024-06-15 |  |  |  | 0 | Not changed yet |  |  | 0 | 30
✎ | Sara Moss - Site Manager | A1380 | Build package 38 | Construction | In Progress | 2024-06-28 | 2024-07-12 | 60 | 2024-06-28 |  |  |  | 0 | Not changed yet |  |  | 0 | 31
✎ | Sara Moss - Site Manager | A1400 | Build package 40 | Construction | Not Started | 2024-08-09 | 2024-08-16 | 0 |  |  |  |  | 0 | Not changed yet |  |  | 0 | 32
✎ | Sara Moss - Site Manager | A1420 | Build package 42 | Construction | Not Started | 2024-08-22 | 2024-08-25 | 0 |  |  |  |  | 0 | Not changed yet |  |  | 0 | 33
✎ | Sara Moss - Site Manager | A1440 | Build package 44 | Construction | Not Started | 2024-09-02 | 2024-09-09 | 0 |  |  |  |  | 0 | Not changed yet |  |  | 0 | 34
✎ | Sara Moss - Site Manager | A1460 | Build package 46 | Construction | Not Started | 2024-09-15 | 2024-09-18 | 0 |  |  |  |  | 0 | Not changed yet |  |  | 0 | 35
✎ | Sara Moss - Site Manager | A1480 | Build package 48 | Construction | Not Started | 2024-09-19 | 2024-10-03 | 0 |  |  |  |  | 0 | Not changed yet |  |  | 0 | 36
✎ | Sara Moss - Site Manager | A1500 | Build package 50 | Construction | Not Started | 2024-10-01 | 2024-10-05 | 0 |  |  |  |  | 0 | Not changed yet |  |  | 0 | 37
✎ | Sara Moss - Site Manager | A1520 | Build package 52 | Construction | Not Started | 2024-10-05 | 2024-10-16 | 0 |  |  |  |  | 0 | Not changed yet |  |  | 0 | 38
✎ | Sara Moss - Site Manager | A1540 | Build package 54 | Construction | Not Started | 2024-11-14 | 2024-11-17 | 0 |  |  |  |  | 0 | Not changed yet |  |  | 0 | 39
✎ | Sara Moss - Site Manager | A1560 | Build package 56 | Construction | Not Started | 2024-11-20 | 2024-12-04 | 0 |  |  |  |  | 0 | Not changed yet |  |  | 0 | 40
✎ | Sara Moss - Site Manager | A1580 | Build package 58 | Construction | Not Started | 2024-11-29 | 2025-02-07 | 0 |  |  |  |  | 0 | Not changed yet |  |  | 0 | 41
✎ | Tom Reid - Package Manager | A1210 | Build package 21 | Construction | Completed | 2024-03-11 | 2024-03-25 | 100 | 2024-03-11 | 2024-03-25 |  |  | 0 | ✓ Complete |  |  | 0 | 42
✎ | Tom Reid - Package Manager | A1230 | Build package 23 | Construction | Completed | 2024-03-25 | 2024-04-05 | 100 | 2024-03-25 | 2024-04-05 |  |  | 0 | ✓ Complete |  |  | 0 | 43
✎ | Tom Reid - Package Manager | A1250 | Build package 25 | Construction | Completed | 2024-05-04 | 2024-05-15 | 100 | 2024-05-04 | 2024-05-15 |  |  | 0 | ✓ Complete |  |  | 0 | 44
✎ | Tom Reid - Package Manager | A1270 | Build package 27 | Construction | Completed | 2024-05-12 | 2024-05-16 | 100 | 2024-05-12 | 2024-05-16 |  |  | 0 | ✓ Complete |  |  | 0 | 45
✎ | Tom Reid - Package Manager | A1290 | Build package 29 | Construction | Completed | 2024-05-24 | 2024-05-27 | 100 | 2024-05-24 | 2024-05-27 |  |  | 0 | ✓ Complete |  |  | 0 | 46
✎ | Tom Reid - Package Manager | A1310 | Build package 31 | Construction | Completed | 2024-06-01 | 2024-06-08 | 100 | 2024-06-01 | 2024-06-08 |  |  | 0 | ✓ Complete |  |  | 0 | 47
✎ | Tom Reid - Package Manager | A1330 | Build package 33 | Construction | Completed | 2024-06-07 | 2024-06-10 | 100 | 2024-06-07 | 2024-06-10 |  |  | 0 | ✓ Complete |  |  | 0 | 48
✎ | Tom Reid - Package Manager | A1350 | Build package 35 | Construction | In Progress | 2024-06-10 | 2024-06-21 | 60 | 2024-06-10 |  |  |  | 0 | Finish date needed |  |  | 0 | 49
✎ | Tom Reid - Package Manager | A1370 | Build package 37 | Construction | In Progress | 2024-06-25 | 2024-07-02 | 40 | 2024-06-25 |  |  |  | 0 | Not changed yet |  |  | 0 | 50
✎ | Tom Reid - Package Manager | A1390 | Build package 39 | Construction | Not Started | 2024-07-05 | 2024-09-13 | 0 |  |  |  |  | 0 | Not changed yet |  |  | 0 | 51
✎ | Tom Reid - Package Manager | A1410 | Build package 41 | Construction | Not Started | 2024-08-12 | 2024-09-02 | 0 |  |  |  |  | 0 | Not changed yet |  |  | 0 | 52
✎ | Tom Reid - Package Manager | A1430 | Build package 43 | Construction | Not Started | 2024-08-23 | 2024-09-13 | 0 |  |  |  |  | 0 | Not changed yet |  |  | 0 | 53
✎ | Tom Reid - Package Manager | A1450 | Build package 45 | Construction | Not Started | 2024-09-05 | 2024-09-26 | 0 |  |  |  |  | 0 | Not changed yet |  |  | 0 | 54
✎ | Tom Reid - Package Manager | A1470 | Build package 47 | Construction | Not Started | 2024-09-16 | 2024-09-23 | 0 |  |  |  |  | 0 | Not changed yet |  |  | 0 | 55
✎ | Tom Reid - Package Manager | A1490 | Build package 49 | Construction | Not Started | 2024-09-26 | 2024-10-07 | 0 |  |  |  |  | 0 | Not changed yet |  |  | 0 | 56
✎ | Tom Reid - Package Manager | A1510 | Build package 51 | Construction | Not Started | 2024-10-03 | 2024-10-07 | 0 |  |  |  |  | 0 | Not changed yet |  |  | 0 | 57
✎ | Tom Reid - Package Manager | A1530 | Build package 53 | Construction | Not Started | 2024-10-10 | 2024-12-19 | 0 |  |  |  |  | 0 | Not changed yet |  |  | 0 | 58
✎ | Tom Reid - Package Manager | A1550 | Build package 55 | Construction | Not Started | 2024-11-15 | 2024-11-26 | 0 |  |  |  |  | 0 | Not changed yet |  |  | 0 | 59
✎ | Tom Reid - Package Manager | A1570 | Build package 57 | Construction | Not Started | 2024-11-27 | 2024-12-01 | 0 |  |  |  |  | 0 | Not changed yet |  |  | 0 | 60
Formulas:
FINISHING LATE = IF([Not yet]="","",INDEX(Data!$H2:H61,[Not yet]))
Complete = IF([Not yet]="","",INDEX(Data!$I2:I61,[Not yet]))
CRITICAL = IF([Not yet]="","",INDEX(Data!$K2:K61,[Not yet]))
Actual finish = IF([Not yet]="","",INDEX(Data!$L2:L61,[Not yet]))

## Dan Lowe
Programme update · Dan Lowe - Design Lead
SAMPLE-FITOUT · data date 30 Jun 2024 · Whole programme
If these figures are struck through, or do not follow what is typed, Excel is calculating manually: press F9 to update them, or turn it on for good with Formulas › Calculation Options › Automatic.
1 Type in the white columns only; grey is the programme, locked. Type dates like 14 Oct 2026. 2 Actual start / finish: dates that have happened - type over the programme's. Not finished yet? Leave Actual finish empty and give an Expected finish. 3 Finishing late? Give a delay cause or a note. Check says what is still needed. |  | ACTIVITIES |  | UPDATED |  | NEED SOMETHING FROM YOU |  |  | FINISHING LATE |  | Grey: the programme | ‹ Overview
|  | 19 |  | 0 |  | 0 |  |  | 0 |  | White: your update | Red in Check: still needed
|  | in this update |  | 0% done |  | red in the Check column |  |  | not finished, past the planned finish |  | Green: you changed it | Bold red ID: critical
THE PROGRAMME (locked) | [5 empty] | YOUR UPDATE | [5 empty] | CHECK
Activity ID | Activity name | Start | Finish | Float (d) | Physical % complete | Actual start | Actual finish | Actual % complete | Expected finish | Delay cause | Notes | Finish moves (d) | Days late | Check | Status | Critical | Planned start | Compare finish | was actual start | was actual finish | was actual % | was expected finish | changed | WBS level | Planned finish
ENG Engineering | [23 empty] | 1
A1010 | Design package 01 | 2024-01-05 | 2024-01-16 | 0 | 100 | 2024-01-05 | 2024-01-16 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-01-05 | 2024-01-16 | 2024-01-05 | 2024-01-16 |  |  | 0 |  | 2024-01-16
A1020 | Design package 02 | 2024-01-10 | 2024-01-13 | 0 | 100 | 2024-01-10 | 2024-01-13 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-01-10 | 2024-01-13 | 2024-01-10 | 2024-01-13 |  |  | 0 |  | 2024-01-13
A1030 | Design package 03 | 2024-01-11 | 2024-01-18 | 0 | 100 | 2024-01-11 | 2024-01-18 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-01-11 | 2024-01-18 | 2024-01-11 | 2024-01-18 |  |  | 0 |  | 2024-01-18
A1040 | Design package 04 | 2024-01-14 | 2024-01-28 | 1 | 100 | 2024-01-14 | 2024-01-28 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-01-14 | 2024-01-28 | 2024-01-14 | 2024-01-28 |  |  | 0 |  | 2024-01-28
A1050 | Design package 05 | 2024-01-21 | 2024-01-24 | 0 | 100 | 2024-01-21 | 2024-01-24 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-01-21 | 2024-01-24 | 2024-01-21 | 2024-01-24 |  |  | 0 |  | 2024-01-24
A1060 | Design package 06 | 2024-01-22 | 2024-02-02 | 50 | 100 | 2024-01-22 | 2024-02-02 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-01-22 | 2024-02-02 | 2024-01-22 | 2024-02-02 |  |  | 0 |  | 2024-02-02
A1070 | Design package 07 | 2024-01-27 | 2024-01-30 | 1 | 100 | 2024-01-27 | 2024-01-30 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-01-27 | 2024-01-30 | 2024-01-27 | 2024-01-30 |  |  | 0 |  | 2024-01-30
A1080 | Design package 08 | 2024-01-28 | 2024-01-31 | 50 | 100 | 2024-01-28 | 2024-01-31 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-01-28 | 2024-01-31 | 2024-01-28 | 2024-01-31 |  |  | 0 |  | 2024-01-31
A1090 | Design package 09 | 2024-01-29 | 2024-02-01 | 0 | 100 | 2024-01-29 | 2024-02-01 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-01-29 | 2024-02-01 | 2024-01-29 | 2024-02-01 |  |  | 0 |  | 2024-02-01
A1100 | Design package 10 | 2024-01-30 | 2024-02-03 | 0 | 100 | 2024-01-30 | 2024-02-03 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-01-30 | 2024-02-03 | 2024-01-30 | 2024-02-03 |  |  | 0 |  | 2024-02-03
A1110 | Design package 11 | 2024-02-01 | 2024-02-15 | 50 | 100 | 2024-02-01 | 2024-02-15 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-02-01 | 2024-02-15 | 2024-02-01 | 2024-02-15 |  |  | 0 |  | 2024-02-15
A1120 | Design package 12 | 2024-02-08 | 2024-02-11 | 1 | 100 | 2024-02-08 | 2024-02-11 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-02-08 | 2024-02-11 | 2024-02-08 | 2024-02-11 |  |  | 0 |  | 2024-02-11
A1130 | Design package 13 | 2024-02-09 | 2024-02-12 | 0 | 100 | 2024-02-09 | 2024-02-12 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-02-09 | 2024-02-12 | 2024-02-09 | 2024-02-12 |  |  | 0 |  | 2024-02-12
A1140 | Design package 14 | 2024-02-10 | 2024-02-17 | 50 | 100 | 2024-02-10 | 2024-02-17 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-02-10 | 2024-02-17 | 2024-02-10 | 2024-02-17 |  |  | 0 |  | 2024-02-17
A1150 | Design package 15 | 2024-02-13 | 2024-02-17 | 0 | 100 | 2024-02-13 | 2024-02-17 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-02-13 | 2024-02-17 | 2024-02-13 | 2024-02-17 |  |  | 0 |  | 2024-02-17
A1160 | Design package 16 | 2024-02-15 | 2024-02-29 | 5 | 100 | 2024-02-15 | 2024-02-29 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-02-15 | 2024-02-29 | 2024-02-15 | 2024-02-29 |  |  | 0 |  | 2024-02-29
A1170 | Design package 17 | 2024-02-22 | 2024-03-07 | 0 | 100 | 2024-02-22 | 2024-03-07 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-02-22 | 2024-03-07 | 2024-02-22 | 2024-03-07 |  |  | 0 |  | 2024-03-07
A1180 | Design package 18 | 2024-02-29 | 2024-03-03 | 1 | 100 | 2024-02-29 | 2024-03-03 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-02-29 | 2024-03-03 | 2024-02-29 | 2024-03-03 |  |  | 0 |  | 2024-03-03
A1190 | Design package 19 | 2024-03-01 | 2024-03-08 | 0 | 100 | 2024-03-01 | 2024-03-08 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-03-01 | 2024-03-08 | 2024-03-01 | 2024-03-08 |  |  | 0 |  | 2024-03-08

## Priya Menon
Programme update · Priya Menon - Project Manager
SAMPLE-FITOUT · data date 30 Jun 2024 · Whole programme
If these figures are struck through, or do not follow what is typed, Excel is calculating manually: press F9 to update them, or turn it on for good with Formulas › Calculation Options › Automatic.
1 Type in the white columns only; grey is the programme, locked. Type dates like 14 Oct 2026. 2 Actual start / finish: dates that have happened - type over the programme's. Not finished yet? Leave Actual finish empty and give an Expected finish. 3 Finishing late? Give a delay cause or a note. Check says what is still needed. |  | ACTIVITIES |  | UPDATED |  | NEED SOMETHING FROM YOU |  |  | FINISHING LATE |  | Grey: the programme | ‹ Overview
|  | 2 |  | 0 |  | 0 |  |  | 0 |  | White: your update | Red in Check: still needed
|  | in this update |  | 0% done |  | red in the Check column |  |  | not finished, past the planned finish |  | Green: you changed it | Bold red ID: critical
THE PROGRAMME (locked) | [5 empty] | YOUR UPDATE | [5 empty] | CHECK
Activity ID | Activity name | Start | Finish | Float (d) | Physical % complete | Actual start | Actual finish | Actual % complete | Expected finish | Delay cause | Notes | Finish moves (d) | Days late | Check | Status | Critical | Planned start | Compare finish | was actual start | was actual finish | was actual % | was expected finish | changed | WBS level | Planned finish
ENG Engineering | [23 empty] | 1
A1000 | Design package 00 | 2024-01-02 | 2024-01-09 | 0 | 100 | 2024-01-02 | 2024-01-09 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-01-02 | 2024-01-09 | 2024-01-02 | 2024-01-09 |  |  | 0 |  | 2024-01-09
CON Construction | [23 empty] | 1
A1590 | Build package 59 | 2025-01-03 | 2025-01-24 | 50 | 0 | [6 empty] | 0 | 0 | Not changed yet | Not Started |  | 2025-01-03 | 2025-01-24 |  |  |  |  | 0 |  | 2025-01-24

## Sara Moss
Programme update · Sara Moss - Site Manager
SAMPLE-FITOUT · data date 30 Jun 2024 · Whole programme
If these figures are struck through, or do not follow what is typed, Excel is calculating manually: press F9 to update them, or turn it on for good with Formulas › Calculation Options › Automatic.
1 Type in the white columns only; grey is the programme, locked. Type dates like 14 Oct 2026. 2 Actual start / finish: dates that have happened - type over the programme's. Not finished yet? Leave Actual finish empty and give an Expected finish. 3 Finishing late? Give a delay cause or a note. Check says what is still needed. |  | ACTIVITIES |  | UPDATED |  | NEED SOMETHING FROM YOU |  |  | FINISHING LATE |  | Grey: the programme | ‹ Overview
|  | 20 |  | 0 |  | 2 |  |  | 0 |  | White: your update | Red in Check: still needed
|  | in this update |  | 0% done |  | red in the Check column |  |  | not finished, past the planned finish |  | Green: you changed it | Bold red ID: critical
THE PROGRAMME (locked) | [5 empty] | YOUR UPDATE | [5 empty] | CHECK
Activity ID | Activity name | Start | Finish | Float (d) | Physical % complete | Actual start | Actual finish | Actual % complete | Expected finish | Delay cause | Notes | Finish moves (d) | Days late | Check | Status | Critical | Planned start | Compare finish | was actual start | was actual finish | was actual % | was expected finish | changed | WBS level | Planned finish
CON Construction | [23 empty] | 1
A1200 | Build package 20 | 2024-03-04 | 2024-03-18 | 0 | 100 | 2024-03-04 | 2024-03-18 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-03-04 | 2024-03-18 | 2024-03-04 | 2024-03-18 |  |  | 0 |  | 2024-03-18
A1220 | Build package 22 | 2024-03-18 | 2024-04-01 | 1 | 100 | 2024-03-18 | 2024-04-01 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-03-18 | 2024-04-01 | 2024-03-18 | 2024-04-01 |  |  | 0 |  | 2024-04-01
A1240 | Build package 24 | 2024-03-30 | 2024-06-08 | 10 | 100 | 2024-03-30 | 2024-06-08 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-03-30 | 2024-06-08 | 2024-03-30 | 2024-06-08 |  |  | 0 |  | 2024-06-08
A1260 | Build package 26 | 2024-05-09 | 2024-05-16 | 5 | 100 | 2024-05-09 | 2024-05-16 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-05-09 | 2024-05-16 | 2024-05-09 | 2024-05-16 |  |  | 0 |  | 2024-05-16
A1280 | Build package 28 | 2024-05-14 | 2024-06-04 | 1 | 100 | 2024-05-14 | 2024-06-04 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-05-14 | 2024-06-04 | 2024-05-14 | 2024-06-04 |  |  | 0 |  | 2024-06-04
A1300 | Build package 30 | 2024-05-25 | 2024-06-08 | -3 | 100 | 2024-05-25 | 2024-06-08 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-05-25 | 2024-06-08 | 2024-05-25 | 2024-06-08 |  |  | 0 |  | 2024-06-08
A1320 | Build package 32 | 2024-06-04 | 2024-06-11 | 0 | 80 | 2024-06-04 | [5 empty] | 0 | 0 | Finish date needed | In Progress | Yes | 2024-06-04 | 2024-06-11 | 2024-06-04 |  |  |  | 0 |  | 2024-06-11
A1340 | Build package 34 | 2024-06-08 | 2024-06-12 | 0 | 40 | 2024-06-08 | [5 empty] | 0 | 0 | Finish date needed | In Progress | Yes | 2024-06-08 | 2024-06-12 | 2024-06-08 |  |  |  | 0 |  | 2024-06-12
A1360 | Build package 36 | 2024-06-15 | 2024-07-06 | 10 | 10 | 2024-06-15 | [5 empty] | 0 | 0 | Not changed yet | In Progress |  | 2024-06-15 | 2024-07-06 | 2024-06-15 |  |  |  | 0 |  | 2024-07-06
A1380 | Build package 38 | 2024-06-28 | 2024-07-12 | 0 | 60 | 2024-06-28 | [5 empty] | 0 | 0 | Not changed yet | In Progress | Yes | 2024-06-28 | 2024-07-12 | 2024-06-28 |  |  |  | 0 |  | 2024-07-12
A1400 | Build package 40 | 2024-08-09 | 2024-08-16 | -3 | 0 | [6 empty] | 0 | 0 | Not changed yet | Not Started | Yes | 2024-08-09 | 2024-08-16 |  |  |  |  | 0 |  | 2024-08-16
A1420 | Build package 42 | 2024-08-22 | 2024-08-25 | 5 | 0 | [6 empty] | 0 | 0 | Not changed yet | Not Started |  | 2024-08-22 | 2024-08-25 |  |  |  |  | 0 |  | 2024-08-25
A1440 | Build package 44 | 2024-09-02 | 2024-09-09 | 50 | 0 | [6 empty] | 0 | 0 | Not changed yet | Not Started |  | 2024-09-02 | 2024-09-09 |  |  |  |  | 0 |  | 2024-09-09
A1460 | Build package 46 | 2024-09-15 | 2024-09-18 | -3 | 0 | [6 empty] | 0 | 0 | Not changed yet | Not Started | Yes | 2024-09-15 | 2024-09-18 |  |  |  |  | 0 |  | 2024-09-18
A1480 | Build package 48 | 2024-09-19 | 2024-10-03 | 0 | 0 | [6 empty] | 0 | 0 | Not changed yet | Not Started | Yes | 2024-09-19 | 2024-10-03 |  |  |  |  | 0 |  | 2024-10-03
A1500 | Build package 50 | 2024-10-01 | 2024-10-05 | 5 | 0 | [6 empty] | 0 | 0 | Not changed yet | Not Started |  | 2024-10-01 | 2024-10-05 |  |  |  |  | 0 |  | 2024-10-05
A1520 | Build package 52 | 2024-10-05 | 2024-10-16 | 50 | 0 | [6 empty] | 0 | 0 | Not changed yet | Not Started |  | 2024-10-05 | 2024-10-16 |  |  |  |  | 0 |  | 2024-10-16
A1540 | Build package 54 | 2024-11-14 | 2024-11-17 | 0 | 0 | [6 empty] | 0 | 0 | Not changed yet | Not Started | Yes | 2024-11-14 | 2024-11-17 |  |  |  |  | 0 |  | 2024-11-17
A1560 | Build package 56 | 2024-11-20 | 2024-12-04 | 5 | 0 | [6 empty] | 0 | 0 | Not changed yet | Not Started |  | 2024-11-20 | 2024-12-04 |  |  |  |  | 0 |  | 2024-12-04
A1580 | Build package 58 | 2024-11-29 | 2025-02-07 | 5 | 0 | [6 empty] | 0 | 0 | Not changed yet | Not Started |  | 2024-11-29 | 2025-02-07 |  |  |  |  | 0 |  | 2025-02-07

## Tom Reid
Programme update · Tom Reid - Package Manager
SAMPLE-FITOUT · data date 30 Jun 2024 · Whole programme
If these figures are struck through, or do not follow what is typed, Excel is calculating manually: press F9 to update them, or turn it on for good with Formulas › Calculation Options › Automatic.
1 Type in the white columns only; grey is the programme, locked. Type dates like 14 Oct 2026. 2 Actual start / finish: dates that have happened - type over the programme's. Not finished yet? Leave Actual finish empty and give an Expected finish. 3 Finishing late? Give a delay cause or a note. Check says what is still needed. |  | ACTIVITIES |  | UPDATED |  | NEED SOMETHING FROM YOU |  |  | FINISHING LATE |  | Grey: the programme | ‹ Overview
|  | 19 |  | 0 |  | 1 |  |  | 0 |  | White: your update | Red in Check: still needed
|  | in this update |  | 0% done |  | red in the Check column |  |  | not finished, past the planned finish |  | Green: you changed it | Bold red ID: critical
THE PROGRAMME (locked) | [5 empty] | YOUR UPDATE | [5 empty] | CHECK
Activity ID | Activity name | Start | Finish | Float (d) | Physical % complete | Actual start | Actual finish | Actual % complete | Expected finish | Delay cause | Notes | Finish moves (d) | Days late | Check | Status | Critical | Planned start | Compare finish | was actual start | was actual finish | was actual % | was expected finish | changed | WBS level | Planned finish
CON Construction | [23 empty] | 1
A1210 | Build package 21 | 2024-03-11 | 2024-03-25 | 0 | 100 | 2024-03-11 | 2024-03-25 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-03-11 | 2024-03-25 | 2024-03-11 | 2024-03-25 |  |  | 0 |  | 2024-03-25
A1230 | Build package 23 | 2024-03-25 | 2024-04-05 | 50 | 100 | 2024-03-25 | 2024-04-05 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-03-25 | 2024-04-05 | 2024-03-25 | 2024-04-05 |  |  | 0 |  | 2024-04-05
A1250 | Build package 25 | 2024-05-04 | 2024-05-15 | -3 | 100 | 2024-05-04 | 2024-05-15 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-05-04 | 2024-05-15 | 2024-05-04 | 2024-05-15 |  |  | 0 |  | 2024-05-15
A1270 | Build package 27 | 2024-05-12 | 2024-05-16 | 0 | 100 | 2024-05-12 | 2024-05-16 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-05-12 | 2024-05-16 | 2024-05-12 | 2024-05-16 |  |  | 0 |  | 2024-05-16
A1290 | Build package 29 | 2024-05-24 | 2024-05-27 | 5 | 100 | 2024-05-24 | 2024-05-27 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-05-24 | 2024-05-27 | 2024-05-24 | 2024-05-27 |  |  | 0 |  | 2024-05-27
A1310 | Build package 31 | 2024-06-01 | 2024-06-08 | -3 | 100 | 2024-06-01 | 2024-06-08 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-06-01 | 2024-06-08 | 2024-06-01 | 2024-06-08 |  |  | 0 |  | 2024-06-08
A1330 | Build package 33 | 2024-06-07 | 2024-06-10 | 50 | 100 | 2024-06-07 | 2024-06-10 |  |  |  |  | 0 | 0 | ✓ Complete | Completed |  | 2024-06-07 | 2024-06-10 | 2024-06-07 | 2024-06-10 |  |  | 0 |  | 2024-06-10
A1350 | Build package 35 | 2024-06-10 | 2024-06-21 | 0 | 60 | 2024-06-10 | [5 empty] | 0 | 0 | Finish date needed | In Progress | Yes | 2024-06-10 | 2024-06-21 | 2024-06-10 |  |  |  | 0 |  | 2024-06-21
A1370 | Build package 37 | 2024-06-25 | 2024-07-02 | -3 | 40 | 2024-06-25 | [5 empty] | 0 | 0 | Not changed yet | In Progress | Yes | 2024-06-25 | 2024-07-02 | 2024-06-25 |  |  |  | 0 |  | 2024-07-02
A1390 | Build package 39 | 2024-07-05 | 2024-09-13 | 0 | 0 | [6 empty] | 0 | 0 | Not changed yet | Not Started | Yes | 2024-07-05 | 2024-09-13 |  |  |  |  | 0 |  | 2024-09-13
A1410 | Build package 41 | 2024-08-12 | 2024-09-02 | 0 | 0 | [6 empty] | 0 | 0 | Not changed yet | Not Started | Yes | 2024-08-12 | 2024-09-02 |  |  |  |  | 0 |  | 2024-09-02
A1430 | Build package 43 | 2024-08-23 | 2024-09-13 | -3 | 0 | [6 empty] | 0 | 0 | Not changed yet | Not Started | Yes | 2024-08-23 | 2024-09-13 |  |  |  |  | 0 |  | 2024-09-13
A1450 | Build package 45 | 2024-09-05 | 2024-09-26 | 10 | 0 | [6 empty] | 0 | 0 | Not changed yet | Not Started |  | 2024-09-05 | 2024-09-26 |  |  |  |  | 0 |  | 2024-09-26
A1470 | Build package 47 | 2024-09-16 | 2024-09-23 | 0 | 0 | [6 empty] | 0 | 0 | Not changed yet | Not Started | Yes | 2024-09-16 | 2024-09-23 |  |  |  |  | 0 |  | 2024-09-23
A1490 | Build package 49 | 2024-09-26 | 2024-10-07 | 0 | 0 | [6 empty] | 0 | 0 | Not changed yet | Not Started | Yes | 2024-09-26 | 2024-10-07 |  |  |  |  | 0 |  | 2024-10-07
A1510 | Build package 51 | 2024-10-03 | 2024-10-07 | 1 | 0 | [6 empty] | 0 | 0 | Not changed yet | Not Started |  | 2024-10-03 | 2024-10-07 |  |  |  |  | 0 |  | 2024-10-07
A1530 | Build package 53 | 2024-10-10 | 2024-12-19 | -3 | 0 | [6 empty] | 0 | 0 | Not changed yet | Not Started | Yes | 2024-10-10 | 2024-12-19 |  |  |  |  | 0 |  | 2024-12-19
A1550 | Build package 55 | 2024-11-15 | 2024-11-26 | 50 | 0 | [6 empty] | 0 | 0 | Not changed yet | Not Started |  | 2024-11-15 | 2024-11-26 |  |  |  |  | 0 |  | 2024-11-26
A1570 | Build package 57 | 2024-11-27 | 2024-12-01 | 50 | 0 | [6 empty] | 0 | 0 | Not changed yet | Not Started |  | 2024-11-27 | 2024-12-01 |  |  |  |  | 0 |  | 2024-12-01

## Resources & cost
Resources & cost
SAMPLE-FITOUT · data date 30 Jun 2024 · Whole programme · resource units and costs to date · costs in USD, as P6 exports them
If these figures are struck through, or do not follow what is typed, Excel is calculating manually: press F9 to update them, or turn it on for good with Formulas › Calculation Options › Automatic.
1 Type over the white cells: totals to date, and what is still to come - costs in USD. 2 Remaining is 0 once the activity has finished. 3 Started or finished an activity on your sheet? Give its actuals here too. |  | ASSIGNMENTS | UPDATED | NEED SOMETHING FROM YOU |  | VARIANCE AT COMPLETION |  | Grey: the programme | [6 empty] | ‹ Overview
|  | 51 | 0 | 0 |  | 0 |  | White: your update
|  | in this update | 0% done | red in the Check column |  | cost: budget less at completion |  | Green: you changed it
THE PROGRAMME (locked) | [6 empty] | YOUR UPDATE (to date) |  |  |  | WORKED OUT
Activity ID | Activity name | Resource | Type | Budget units | Budget cost | Price / unit | Actual units to date | Remaining units | Actual cost to date | Remaining cost | At completion units | Units variance | At completion cost | Cost variance | Check | was actual units | was remaining units | was actual cost | was remaining cost | Assignment | Cost from units | Started | Finished | Progress given | Changed
Dan Lowe - Design Lead
A1010 | Design package 01 | Site Labour | Labour · h | 64 | 4800 | 0 | 64 | 0 | 4800 | 0 | 64 | 0 | 4800 | 0 | Not changed yet | 64 | 0 | 4800 | 0 | 7001 | 0 | 1 | 1 | 0 | 0
A1020 | Design package 02 | Bulk Materials | Material · units | 16 | 1520 | 0 | 16 | 0 | 1520 | 0 | 16 | 0 | 1520 | 0 | Not changed yet | 16 | 0 | 1520 | 0 | 7002 | 0 | 1 | 1 | 0 | 0
A1040 | Design package 04 | Site Labour | Labour · h | 80 | 6000 | 0 | 80 | 0 | 6000 | 0 | 80 | 0 | 6000 | 0 | Not changed yet | 80 | 0 | 6000 | 0 | 7004 | 0 | 1 | 1 | 0 | 0
A1050 | Design package 05 | Bulk Materials | Material · units | 16 | 1520 | 0 | 16 | 0 | 1520 | 0 | 16 | 0 | 1520 | 0 | Not changed yet | 16 | 0 | 1520 | 0 | 7005 | 0 | 1 | 1 | 0 | 0
A1060 | Design package 06 | Design Engineer | Labour · h | 64 | 3520 | 0 | 64 | 0 | 3520 | 0 | 64 | 0 | 3520 | 0 | Not changed yet | 64 | 0 | 3520 | 0 | 7006 | 0 | 1 | 1 | 0 | 0
A1070 | Design package 07 | Site Labour | Labour · h | 16 | 1200 | 0 | 16 | 0 | 1200 | 0 | 16 | 0 | 1200 | 0 | Not changed yet | 16 | 0 | 1200 | 0 | 7007 | 0 | 1 | 1 | 0 | 0
A1080 | Design package 08 | Bulk Materials | Material · units | 16 | 1520 | 0 | 16 | 0 | 1520 | 0 | 16 | 0 | 1520 | 0 | Not changed yet | 16 | 0 | 1520 | 0 | 7008 | 0 | 1 | 1 | 0 | 0
A1090 | Design package 09 | Design Engineer | Labour · h | 16 | 880 | 0 | 16 | 0 | 880 | 0 | 16 | 0 | 880 | 0 | Not changed yet | 16 | 0 | 880 | 0 | 7009 | 0 | 1 | 1 | 0 | 0
A1110 | Design package 11 | Bulk Materials | Material · units | 80 | 7600 | 0 | 80 | 0 | 7600 | 0 | 80 | 0 | 7600 | 0 | Not changed yet | 80 | 0 | 7600 | 0 | 7011 | 0 | 1 | 1 | 0 | 0
A1120 | Design package 12 | Design Engineer | Labour · h | 16 | 880 | 0 | 16 | 0 | 880 | 0 | 16 | 0 | 880 | 0 | Not changed yet | 16 | 0 | 880 | 0 | 7012 | 0 | 1 | 1 | 0 | 0
A1130 | Design package 13 | Site Labour | Labour · h | 16 | 1200 | 0 | 16 | 0 | 1200 | 0 | 16 | 0 | 1200 | 0 | Not changed yet | 16 | 0 | 1200 | 0 | 7013 | 0 | 1 | 1 | 0 | 0
A1140 | Design package 14 | Bulk Materials | Material · units | 40 | 3800 | 0 | 40 | 0 | 3800 | 0 | 40 | 0 | 3800 | 0 | Not changed yet | 40 | 0 | 3800 | 0 | 7014 | 0 | 1 | 1 | 0 | 0
A1150 | Design package 15 | Design Engineer | Labour · h | 24 | 1320 | 0 | 24 | 0 | 1320 | 0 | 24 | 0 | 1320 | 0 | Not changed yet | 24 | 0 | 1320 | 0 | 7015 | 0 | 1 | 1 | 0 | 0
A1160 | Design package 16 | Site Labour | Labour · h | 80 | 6000 | 0 | 80 | 0 | 6000 | 0 | 80 | 0 | 6000 | 0 | Not changed yet | 80 | 0 | 6000 | 0 | 7016 | 0 | 1 | 1 | 0 | 0
A1180 | Design package 18 | Design Engineer | Labour · h | 16 | 880 | 0 | 16 | 0 | 880 | 0 | 16 | 0 | 880 | 0 | Not changed yet | 16 | 0 | 880 | 0 | 7018 | 0 | 1 | 1 | 0 | 0
A1190 | Design package 19 | Site Labour | Labour · h | 40 | 3000 | 0 | 40 | 0 | 3000 | 0 | 40 | 0 | 3000 | 0 | Not changed yet | 40 | 0 | 3000 | 0 | 7019 | 0 | 1 | 1 | 0 | 0
Priya Menon - Project Manager
A1000 | Design package 00 | Design Engineer | Labour · h | 40 | 2200 | 0 | 40 | 0 | 2200 | 0 | 40 | 0 | 2200 | 0 | Not changed yet | 40 | 0 | 2200 | 0 | 7000 | 0 | 1 | 1 | 0 | 0
Sara Moss - Site Manager
A1200 | Build package 20 | Bulk Materials | Material · units | 80 | 7600 | 0 | 80 | 0 | 7600 | 0 | 80 | 0 | 7600 | 0 | Not changed yet | 80 | 0 | 7600 | 0 | 7020 | 0 | 1 | 1 | 0 | 0
A1220 | Build package 22 | Site Labour | Labour · h | 80 | 6000 | 0 | 80 | 0 | 6000 | 0 | 80 | 0 | 6000 | 0 | Not changed yet | 80 | 0 | 6000 | 0 | 7022 | 0 | 1 | 1 | 0 | 0
A1260 | Build package 26 | Bulk Materials | Material · units | 40 | 3800 | 0 | 40 | 0 | 3800 | 0 | 40 | 0 | 3800 | 0 | Not changed yet | 40 | 0 | 3800 | 0 | 7026 | 0 | 1 | 1 | 0 | 0
A1280 | Build package 28 | Site Labour | Labour · h | 120 | 9000 | 0 | 120 | 0 | 9000 | 0 | 120 | 0 | 9000 | 0 | Not changed yet | 120 | 0 | 9000 | 0 | 7028 | 0 | 1 | 1 | 0 | 0
A1300 | Build package 30 | Design Engineer | Labour · h | 80 | 4400 | 0 | 80 | 0 | 4400 | 0 | 80 | 0 | 4400 | 0 | Not changed yet | 80 | 0 | 4400 | 0 | 7030 | 0 | 1 | 1 | 0 | 0
A1320 | Build package 32 | Bulk Materials | Material · units | 40 | 3800 | 0 | 32 | 8 | 3040 | 760 | 40 | 0 | 3800 | 0 | Not changed yet | 32 | 8 | 3040 | 760 | 7032 | 0 | 1 | 0 | 0 | 0
A1340 | Build package 34 | Site Labour | Labour · h | 24 | 1800 | 0 | 9.6 | 14.4 | 720 | 1080 | 24 | 0 | 1800 | 0 | Not changed yet | 9.6 | 14.4 | 720 | 1080 | 7034 | 0 | 1 | 0 | 0 | 0
A1360 | Build package 36 | Design Engineer | Labour · h | 120 | 6600 | 0 | 12 | 108 | 660 | 5940 | 120 | 0 | 6600 | 0 | Not changed yet | 12 | 108 | 660 | 5940 | 7036 | 0 | 1 | 0 | 0 | 0
A1400 | Build package 40 | Site Labour | Labour · h | 40 | 3000 | 0 | 0 | 40 | 0 | 3000 | 40 | 0 | 3000 | 0 | Not changed yet | 0 | 40 | 0 | 3000 | 7040 | 0 | 0 | 0 | 0 | 0
A1420 | Build package 42 | Design Engineer | Labour · h | 16 | 880 | 0 | 0 | 16 | 0 | 880 | 16 | 0 | 880 | 0 | Not changed yet | 0 | 16 | 0 | 880 | 7042 | 0 | 0 | 0 | 0 | 0
A1440 | Build package 44 | Bulk Materials | Material · units | 40 | 3800 | 0 | 0 | 40 | 0 | 3800 | 40 | 0 | 3800 | 0 | Not changed yet | 0 | 40 | 0 | 3800 | 7044 | 0 | 0 | 0 | 0 | 0
A1460 | Build package 46 | Site Labour | Labour · h | 16 | 1200 | 0 | 0 | 16 | 0 | 1200 | 16 | 0 | 1200 | 0 | Not changed yet | 0 | 16 | 0 | 1200 | 7046 | 0 | 0 | 0 | 0 | 0
A1480 | Build package 48 | Design Engineer | Labour · h | 80 | 4400 | 0 | 0 | 80 | 0 | 4400 | 80 | 0 | 4400 | 0 | Not changed yet | 0 | 80 | 0 | 4400 | 7048 | 0 | 0 | 0 | 0 | 0
A1500 | Build package 50 | Bulk Materials | Material · units | 24 | 2280 | 0 | 0 | 24 | 0 | 2280 | 24 | 0 | 2280 | 0 | Not changed yet | 0 | 24 | 0 | 2280 | 7050 | 0 | 0 | 0 | 0 | 0
A1540 | Build package 54 | Design Engineer | Labour · h | 16 | 880 | 0 | 0 | 16 | 0 | 880 | 16 | 0 | 880 | 0 | Not changed yet | 0 | 16 | 0 | 880 | 7054 | 0 | 0 | 0 | 0 | 0
A1560 | Build package 56 | Bulk Materials | Material · units | 80 | 7600 | 0 | 0 | 80 | 0 | 7600 | 80 | 0 | 7600 | 0 | Not changed yet | 0 | 80 | 0 | 7600 | 7056 | 0 | 0 | 0 | 0 | 0
A1580 | Build package 58 | Site Labour | Labour · h | 400 | 30000 | 0 | 0 | 400 | 0 | 30000 | 400 | 0 | 30000 | 0 | Not changed yet | 0 | 400 | 0 | 30000 | 7058 | 0 | 0 | 0 | 0 | 0
Tom Reid - Package Manager
A1210 | Build package 21 | Design Engineer | Labour · h | 80 | 4400 | 0 | 80 | 0 | 4400 | 0 | 80 | 0 | 4400 | 0 | Not changed yet | 80 | 0 | 4400 | 0 | 7021 | 0 | 1 | 1 | 0 | 0
A1230 | Build package 23 | Bulk Materials | Material · units | 64 | 6080 | 0 | 64 | 0 | 6080 | 0 | 64 | 0 | 6080 | 0 | Not changed yet | 64 | 0 | 6080 | 0 | 7023 | 0 | 1 | 1 | 0 | 0
A1250 | Build package 25 | Site Labour | Labour · h | 64 | 4800 | 0 | 64 | 0 | 4800 | 0 | 64 | 0 | 4800 | 0 | Not changed yet | 64 | 0 | 4800 | 0 | 7025 | 0 | 1 | 1 | 0 | 0
A1270 | Build package 27 | Design Engineer | Labour · h | 24 | 1320 | 0 | 24 | 0 | 1320 | 0 | 24 | 0 | 1320 | 0 | Not changed yet | 24 | 0 | 1320 | 0 | 7027 | 0 | 1 | 1 | 0 | 0
A1290 | Build package 29 | Bulk Materials | Material · units | 16 | 1520 | 0 | 16 | 0 | 1520 | 0 | 16 | 0 | 1520 | 0 | Not changed yet | 16 | 0 | 1520 | 0 | 7029 | 0 | 1 | 1 | 0 | 0
A1330 | Build package 33 | Design Engineer | Labour · h | 16 | 880 | 0 | 16 | 0 | 880 | 0 | 16 | 0 | 880 | 0 | Not changed yet | 16 | 0 | 880 | 0 | 7033 | 0 | 1 | 1 | 0 | 0
A1350 | Build package 35 | Bulk Materials | Material · units | 64 | 6080 | 0 | 38.4 | 25.6 | 3648 | 2432 | 64 | 0 | 6080 | 0 | Not changed yet | 38.4 | 25.6 | 3648 | 2432 | 7035 | 0 | 1 | 0 | 0 | 0
A1370 | Build package 37 | Site Labour | Labour · h | 40 | 3000 | 0 | 16 | 24 | 1200 | 1800 | 40 | 0 | 3000 | 0 | Not changed yet | 16 | 24 | 1200 | 1800 | 7037 | 0 | 1 | 0 | 0 | 0
A1390 | Build package 39 | Design Engineer | Labour · h | 400 | 22000 | 0 | 0 | 400 | 0 | 22000 | 400 | 0 | 22000 | 0 | Not changed yet | 0 | 400 | 0 | 22000 | 7039 | 0 | 0 | 0 | 0 | 0
A1410 | Build package 41 | Bulk Materials | Material · units | 120 | 11400 | 0 | 0 | 120 | 0 | 11400 | 120 | 0 | 11400 | 0 | Not changed yet | 0 | 120 | 0 | 11400 | 7041 | 0 | 0 | 0 | 0 | 0
A1430 | Build package 43 | Site Labour | Labour · h | 120 | 9000 | 0 | 0 | 120 | 0 | 9000 | 120 | 0 | 9000 | 0 | Not changed yet | 0 | 120 | 0 | 9000 | 7043 | 0 | 0 | 0 | 0 | 0
A1470 | Build package 47 | Bulk Materials | Material · units | 40 | 3800 | 0 | 0 | 40 | 0 | 3800 | 40 | 0 | 3800 | 0 | Not changed yet | 0 | 40 | 0 | 3800 | 7047 | 0 | 0 | 0 | 0 | 0
A1490 | Build package 49 | Site Labour | Labour · h | 64 | 4800 | 0 | 0 | 64 | 0 | 4800 | 64 | 0 | 4800 | 0 | Not changed yet | 0 | 64 | 0 | 4800 | 7049 | 0 | 0 | 0 | 0 | 0
A1510 | Build package 51 | Design Engineer | Labour · h | 24 | 1320 | 0 | 0 | 24 | 0 | 1320 | 24 | 0 | 1320 | 0 | Not changed yet | 0 | 24 | 0 | 1320 | 7051 | 0 | 0 | 0 | 0 | 0
A1530 | Build package 53 | Bulk Materials | Material · units | 400 | 38000 | 0 | 0 | 400 | 0 | 38000 | 400 | 0 | 38000 | 0 | Not changed yet | 0 | 400 | 0 | 38000 | 7053 | 0 | 0 | 0 | 0 | 0
A1550 | Build package 55 | Site Labour | Labour · h | 64 | 4800 | 0 | 0 | 64 | 0 | 4800 | 64 | 0 | 4800 | 0 | Not changed yet | 0 | 64 | 0 | 4800 | 7055 | 0 | 0 | 0 | 0 | 0
A1570 | Build package 57 | Design Engineer | Labour · h | 24 | 1320 | 0 | 0 | 24 | 0 | 1320 | 24 | 0 | 1320 | 0 | Not changed yet | 0 | 24 | 0 | 1320 | 7057 | 0 | 0 | 0 | 0 | 0

## All updates
All updates
SAMPLE-FITOUT · data date 30 Jun 2024 · Whole programme · every activity with what was entered, ready to key into P6
Responsible Person | Activity ID | Activity name | Status | Planned start | Planned finish | Start | Finish | Physical % complete | Actual start | Actual finish | Actual % complete | Expected finish | Finish moves (d) | Days late | Check | Delay cause | Notes | Updated
Dan Lowe - Design Lead | A1010 | Design package 01 | Completed | 2024-01-05 | 2024-01-16 | 2024-01-05 | 2024-01-16 | 100 | 2024-01-05 | 2024-01-16 |  |  | 0 | 0 | ✓ Complete
Dan Lowe - Design Lead | A1020 | Design package 02 | Completed | 2024-01-10 | 2024-01-13 | 2024-01-10 | 2024-01-13 | 100 | 2024-01-10 | 2024-01-13 |  |  | 0 | 0 | ✓ Complete
Dan Lowe - Design Lead | A1030 | Design package 03 | Completed | 2024-01-11 | 2024-01-18 | 2024-01-11 | 2024-01-18 | 100 | 2024-01-11 | 2024-01-18 |  |  | 0 | 0 | ✓ Complete
Dan Lowe - Design Lead | A1040 | Design package 04 | Completed | 2024-01-14 | 2024-01-28 | 2024-01-14 | 2024-01-28 | 100 | 2024-01-14 | 2024-01-28 |  |  | 0 | 0 | ✓ Complete
Dan Lowe - Design Lead | A1050 | Design package 05 | Completed | 2024-01-21 | 2024-01-24 | 2024-01-21 | 2024-01-24 | 100 | 2024-01-21 | 2024-01-24 |  |  | 0 | 0 | ✓ Complete
Dan Lowe - Design Lead | A1060 | Design package 06 | Completed | 2024-01-22 | 2024-02-02 | 2024-01-22 | 2024-02-02 | 100 | 2024-01-22 | 2024-02-02 |  |  | 0 | 0 | ✓ Complete
Dan Lowe - Design Lead | A1070 | Design package 07 | Completed | 2024-01-27 | 2024-01-30 | 2024-01-27 | 2024-01-30 | 100 | 2024-01-27 | 2024-01-30 |  |  | 0 | 0 | ✓ Complete
Dan Lowe - Design Lead | A1080 | Design package 08 | Completed | 2024-01-28 | 2024-01-31 | 2024-01-28 | 2024-01-31 | 100 | 2024-01-28 | 2024-01-31 |  |  | 0 | 0 | ✓ Complete
Dan Lowe - Design Lead | A1090 | Design package 09 | Completed | 2024-01-29 | 2024-02-01 | 2024-01-29 | 2024-02-01 | 100 | 2024-01-29 | 2024-02-01 |  |  | 0 | 0 | ✓ Complete
Dan Lowe - Design Lead | A1100 | Design package 10 | Completed | 2024-01-30 | 2024-02-03 | 2024-01-30 | 2024-02-03 | 100 | 2024-01-30 | 2024-02-03 |  |  | 0 | 0 | ✓ Complete
Dan Lowe - Design Lead | A1110 | Design package 11 | Completed | 2024-02-01 | 2024-02-15 | 2024-02-01 | 2024-02-15 | 100 | 2024-02-01 | 2024-02-15 |  |  | 0 | 0 | ✓ Complete
Dan Lowe - Design Lead | A1120 | Design package 12 | Completed | 2024-02-08 | 2024-02-11 | 2024-02-08 | 2024-02-11 | 100 | 2024-02-08 | 2024-02-11 |  |  | 0 | 0 | ✓ Complete
Dan Lowe - Design Lead | A1130 | Design package 13 | Completed | 2024-02-09 | 2024-02-12 | 2024-02-09 | 2024-02-12 | 100 | 2024-02-09 | 2024-02-12 |  |  | 0 | 0 | ✓ Complete
Dan Lowe - Design Lead | A1140 | Design package 14 | Completed | 2024-02-10 | 2024-02-17 | 2024-02-10 | 2024-02-17 | 100 | 2024-02-10 | 2024-02-17 |  |  | 0 | 0 | ✓ Complete
Dan Lowe - Design Lead | A1150 | Design package 15 | Completed | 2024-02-13 | 2024-02-17 | 2024-02-13 | 2024-02-17 | 100 | 2024-02-13 | 2024-02-17 |  |  | 0 | 0 | ✓ Complete
Dan Lowe - Design Lead | A1160 | Design package 16 | Completed | 2024-02-15 | 2024-02-29 | 2024-02-15 | 2024-02-29 | 100 | 2024-02-15 | 2024-02-29 |  |  | 0 | 0 | ✓ Complete
Dan Lowe - Design Lead | A1170 | Design package 17 | Completed | 2024-02-22 | 2024-03-07 | 2024-02-22 | 2024-03-07 | 100 | 2024-02-22 | 2024-03-07 |  |  | 0 | 0 | ✓ Complete
Dan Lowe - Design Lead | A1180 | Design package 18 | Completed | 2024-02-29 | 2024-03-03 | 2024-02-29 | 2024-03-03 | 100 | 2024-02-29 | 2024-03-03 |  |  | 0 | 0 | ✓ Complete
Dan Lowe - Design Lead | A1190 | Design package 19 | Completed | 2024-03-01 | 2024-03-08 | 2024-03-01 | 2024-03-08 | 100 | 2024-03-01 | 2024-03-08 |  |  | 0 | 0 | ✓ Complete
Priya Menon - Project Manager | A1000 | Design package 00 | Completed | 2024-01-02 | 2024-01-09 | 2024-01-02 | 2024-01-09 | 100 | 2024-01-02 | 2024-01-09 |  |  | 0 | 0 | ✓ Complete
Priya Menon - Project Manager | A1590 | Build package 59 | Not Started | 2025-01-03 | 2025-01-24 | 2025-01-03 | 2025-01-24 | 0 |  |  |  |  | 0 | 0 | Not changed yet
Sara Moss - Site Manager | A1200 | Build package 20 | Completed | 2024-03-04 | 2024-03-18 | 2024-03-04 | 2024-03-18 | 100 | 2024-03-04 | 2024-03-18 |  |  | 0 | 0 | ✓ Complete
Sara Moss - Site Manager | A1220 | Build package 22 | Completed | 2024-03-18 | 2024-04-01 | 2024-03-18 | 2024-04-01 | 100 | 2024-03-18 | 2024-04-01 |  |  | 0 | 0 | ✓ Complete
Sara Moss - Site Manager | A1240 | Build package 24 | Completed | 2024-03-30 | 2024-06-08 | 2024-03-30 | 2024-06-08 | 100 | 2024-03-30 | 2024-06-08 |  |  | 0 | 0 | ✓ Complete
Sara Moss - Site Manager | A1260 | Build package 26 | Completed | 2024-05-09 | 2024-05-16 | 2024-05-09 | 2024-05-16 | 100 | 2024-05-09 | 2024-05-16 |  |  | 0 | 0 | ✓ Complete
Sara Moss - Site Manager | A1280 | Build package 28 | Completed | 2024-05-14 | 2024-06-04 | 2024-05-14 | 2024-06-04 | 100 | 2024-05-14 | 2024-06-04 |  |  | 0 | 0 | ✓ Complete
Sara Moss - Site Manager | A1300 | Build package 30 | Completed | 2024-05-25 | 2024-06-08 | 2024-05-25 | 2024-06-08 | 100 | 2024-05-25 | 2024-06-08 |  |  | 0 | 0 | ✓ Complete
Sara Moss - Site Manager | A1320 | Build package 32 | In Progress | 2024-06-04 | 2024-06-11 | 2024-06-04 | 2024-06-11 | 80 | 2024-06-04 |  |  |  | 0 | 0 | Finish date needed
Sara Moss - Site Manager | A1340 | Build package 34 | In Progress | 2024-06-08 | 2024-06-12 | 2024-06-08 | 2024-06-12 | 40 | 2024-06-08 |  |  |  | 0 | 0 | Finish date needed
Sara Moss - Site Manager | A1360 | Build package 36 | In Progress | 2024-06-15 | 2024-07-06 | 2024-06-15 | 2024-07-06 | 10 | 2024-06-15 |  |  |  | 0 | 0 | Not changed yet
Sara Moss - Site Manager | A1380 | Build package 38 | In Progress | 2024-06-28 | 2024-07-12 | 2024-06-28 | 2024-07-12 | 60 | 2024-06-28 |  |  |  | 0 | 0 | Not changed yet
Sara Moss - Site Manager | A1400 | Build package 40 | Not Started | 2024-08-09 | 2024-08-16 | 2024-08-09 | 2024-08-16 | 0 |  |  |  |  | 0 | 0 | Not changed yet
Sara Moss - Site Manager | A1420 | Build package 42 | Not Started | 2024-08-22 | 2024-08-25 | 2024-08-22 | 2024-08-25 | 0 |  |  |  |  | 0 | 0 | Not changed yet
Sara Moss - Site Manager | A1440 | Build package 44 | Not Started | 2024-09-02 | 2024-09-09 | 2024-09-02 | 2024-09-09 | 0 |  |  |  |  | 0 | 0 | Not changed yet
Sara Moss - Site Manager | A1460 | Build package 46 | Not Started | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-18 | 0 |  |  |  |  | 0 | 0 | Not changed yet
Sara Moss - Site Manager | A1480 | Build package 48 | Not Started | 2024-09-19 | 2024-10-03 | 2024-09-19 | 2024-10-03 | 0 |  |  |  |  | 0 | 0 | Not changed yet
Sara Moss - Site Manager | A1500 | Build package 50 | Not Started | 2024-10-01 | 2024-10-05 | 2024-10-01 | 2024-10-05 | 0 |  |  |  |  | 0 | 0 | Not changed yet
Sara Moss - Site Manager | A1520 | Build package 52 | Not Started | 2024-10-05 | 2024-10-16 | 2024-10-05 | 2024-10-16 | 0 |  |  |  |  | 0 | 0 | Not changed yet
Sara Moss - Site Manager | A1540 | Build package 54 | Not Started | 2024-11-14 | 2024-11-17 | 2024-11-14 | 2024-11-17 | 0 |  |  |  |  | 0 | 0 | Not changed yet
Sara Moss - Site Manager | A1560 | Build package 56 | Not Started | 2024-11-20 | 2024-12-04 | 2024-11-20 | 2024-12-04 | 0 |  |  |  |  | 0 | 0 | Not changed yet
Sara Moss - Site Manager | A1580 | Build package 58 | Not Started | 2024-11-29 | 2025-02-07 | 2024-11-29 | 2025-02-07 | 0 |  |  |  |  | 0 | 0 | Not changed yet
Tom Reid - Package Manager | A1210 | Build package 21 | Completed | 2024-03-11 | 2024-03-25 | 2024-03-11 | 2024-03-25 | 100 | 2024-03-11 | 2024-03-25 |  |  | 0 | 0 | ✓ Complete
Tom Reid - Package Manager | A1230 | Build package 23 | Completed | 2024-03-25 | 2024-04-05 | 2024-03-25 | 2024-04-05 | 100 | 2024-03-25 | 2024-04-05 |  |  | 0 | 0 | ✓ Complete
Tom Reid - Package Manager | A1250 | Build package 25 | Completed | 2024-05-04 | 2024-05-15 | 2024-05-04 | 2024-05-15 | 100 | 2024-05-04 | 2024-05-15 |  |  | 0 | 0 | ✓ Complete
Tom Reid - Package Manager | A1270 | Build package 27 | Completed | 2024-05-12 | 2024-05-16 | 2024-05-12 | 2024-05-16 | 100 | 2024-05-12 | 2024-05-16 |  |  | 0 | 0 | ✓ Complete
Tom Reid - Package Manager | A1290 | Build package 29 | Completed | 2024-05-24 | 2024-05-27 | 2024-05-24 | 2024-05-27 | 100 | 2024-05-24 | 2024-05-27 |  |  | 0 | 0 | ✓ Complete
Tom Reid - Package Manager | A1310 | Build package 31 | Completed | 2024-06-01 | 2024-06-08 | 2024-06-01 | 2024-06-08 | 100 | 2024-06-01 | 2024-06-08 |  |  | 0 | 0 | ✓ Complete
Tom Reid - Package Manager | A1330 | Build package 33 | Completed | 2024-06-07 | 2024-06-10 | 2024-06-07 | 2024-06-10 | 100 | 2024-06-07 | 2024-06-10 |  |  | 0 | 0 | ✓ Complete
Tom Reid - Package Manager | A1350 | Build package 35 | In Progress | 2024-06-10 | 2024-06-21 | 2024-06-10 | 2024-06-21 | 60 | 2024-06-10 |  |  |  | 0 | 0 | Finish date needed
Tom Reid - Package Manager | A1370 | Build package 37 | In Progress | 2024-06-25 | 2024-07-02 | 2024-06-25 | 2024-07-02 | 40 | 2024-06-25 |  |  |  | 0 | 0 | Not changed yet
Tom Reid - Package Manager | A1390 | Build package 39 | Not Started | 2024-07-05 | 2024-09-13 | 2024-07-05 | 2024-09-13 | 0 |  |  |  |  | 0 | 0 | Not changed yet
Tom Reid - Package Manager | A1410 | Build package 41 | Not Started | 2024-08-12 | 2024-09-02 | 2024-08-12 | 2024-09-02 | 0 |  |  |  |  | 0 | 0 | Not changed yet
Tom Reid - Package Manager | A1430 | Build package 43 | Not Started | 2024-08-23 | 2024-09-13 | 2024-08-23 | 2024-09-13 | 0 |  |  |  |  | 0 | 0 | Not changed yet
Tom Reid - Package Manager | A1450 | Build package 45 | Not Started | 2024-09-05 | 2024-09-26 | 2024-09-05 | 2024-09-26 | 0 |  |  |  |  | 0 | 0 | Not changed yet
Tom Reid - Package Manager | A1470 | Build package 47 | Not Started | 2024-09-16 | 2024-09-23 | 2024-09-16 | 2024-09-23 | 0 |  |  |  |  | 0 | 0 | Not changed yet
Tom Reid - Package Manager | A1490 | Build package 49 | Not Started | 2024-09-26 | 2024-10-07 | 2024-09-26 | 2024-10-07 | 0 |  |  |  |  | 0 | 0 | Not changed yet
Tom Reid - Package Manager | A1510 | Build package 51 | Not Started | 2024-10-03 | 2024-10-07 | 2024-10-03 | 2024-10-07 | 0 |  |  |  |  | 0 | 0 | Not changed yet
Tom Reid - Package Manager | A1530 | Build package 53 | Not Started | 2024-10-10 | 2024-12-19 | 2024-10-10 | 2024-12-19 | 0 |  |  |  |  | 0 | 0 | Not changed yet
Tom Reid - Package Manager | A1550 | Build package 55 | Not Started | 2024-11-15 | 2024-11-26 | 2024-11-15 | 2024-11-26 | 0 |  |  |  |  | 0 | 0 | Not changed yet
Tom Reid - Package Manager | A1570 | Build package 57 | Not Started | 2024-11-27 | 2024-12-01 | 2024-11-27 | 2024-12-01 | 0 |  |  |  |  | 0 | 0 | Not changed yet

## Guide
How to use this workbook
To update your activities
1. Go to the sheet with your name on its tab, or click your name on the Overview.
2. Grey columns are the programme: start, finish, float and physical % complete. They are locked, for reference. Activities in bold red are critical.
3. Fill in the white columns. What you change turns green.
Actual start / Actual finish - hold the programme's dates: type over them with the date the work really started or finished. A date in the future is refused.
Actual % complete - starts empty: how complete the activity actually is now, 0 to 100.
Expected finish - only if the finish date is changing: when you now expect it to finish. Leave it empty if the programme's Finish still holds.
Delay cause - if it is late or moving, pick the main cause from the arrow (or type your own); add a note on what is being done.
4. Finish moves shows how far your dates move the finish; Days late is how far past the planned finish it now ends (calendar days).
5. Look at the Check column. Anything in red still needs something from you:
Reason needed - it finishes after the planned finish: give a delay cause or a note.
Start date needed - it should have started by the data date, or you have given progress: give the actual start.
Finish date needed - the finish date is already past: give the actual finish, or an expected finish.
Date in the future - an actual date cannot be later than today.
6. Save the file and send it back.
Resources and costs
This programme carries resource units and costs, so the Resources & cost sheet lists every resource on your activities.
Actual to date - type over it with the total booked so far, across all periods: hours for labour and plant, quantities for materials, money for costs (in USD, the currency P6 exports costs in - convert if you work in another).
Remaining - what is still to come from now on. Re-estimate it if the work will take more or less than planned; once an activity has finished it is 0.
At completion is actual plus remaining; Variance is the budget less that, so an overrun shows red and negative.
Check: Start date needed - actuals on an activity with no actual start on your sheet. Remaining on finished work - set it to 0, or move it into the actual. Actuals not given - you started or progressed the activity but booked nothing to it. Actual reduced and Over budget are worth a second look.
For the planner
The Overview's drop-downs choose one person or everyone, and what to show: everything, what needs attention, what has not been updated yet, what is late or critical, or by status. Find narrows the list to an ID, a name or a WBS. The table shows whose update has come back; click a name to open their sheet, or ✎ in the list to go to that row.
All updates lists every activity with what was entered. When the workbooks come back, read them in the app (Progress Update, Apply progress): it checks every entry, merges everyone's files and creates one XER that brings every update into P6, notes included.
The sheets are protected without a password so formulas are not overwritten by accident. Review ▸ Unprotect Sheet removes it.
Figures struck through, or not following what is typed? Excel is calculating manually - it takes that from the first workbook it opened. Press F9 to update, or Formulas ▸ Calculation Options ▸ Automatic to keep it up to date.

## Data (hidden)
Person | Sheet | Row | Activity ID | Activity name | WBS | Status | Start | Finish | Physical % | Actual start | Actual finish | Actual % | Expected finish | Days late | Check | Notes | Changed | Critical | Person shown | Shown | Count | Delay cause
Dan Lowe - Design Lead | Dan Lowe | 11 | A1010 | Design package 01 | Engineering | Completed | 2024-01-05 | 2024-01-16 | 100 | 2024-01-05 | 2024-01-16 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 1
Dan Lowe - Design Lead | Dan Lowe | 12 | A1020 | Design package 02 | Engineering | Completed | 2024-01-10 | 2024-01-13 | 100 | 2024-01-10 | 2024-01-13 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 2
Dan Lowe - Design Lead | Dan Lowe | 13 | A1030 | Design package 03 | Engineering | Completed | 2024-01-11 | 2024-01-18 | 100 | 2024-01-11 | 2024-01-18 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 3
Dan Lowe - Design Lead | Dan Lowe | 14 | A1040 | Design package 04 | Engineering | Completed | 2024-01-14 | 2024-01-28 | 100 | 2024-01-14 | 2024-01-28 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 4
Dan Lowe - Design Lead | Dan Lowe | 15 | A1050 | Design package 05 | Engineering | Completed | 2024-01-21 | 2024-01-24 | 100 | 2024-01-21 | 2024-01-24 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 5
Dan Lowe - Design Lead | Dan Lowe | 16 | A1060 | Design package 06 | Engineering | Completed | 2024-01-22 | 2024-02-02 | 100 | 2024-01-22 | 2024-02-02 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 6
Dan Lowe - Design Lead | Dan Lowe | 17 | A1070 | Design package 07 | Engineering | Completed | 2024-01-27 | 2024-01-30 | 100 | 2024-01-27 | 2024-01-30 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 7
Dan Lowe - Design Lead | Dan Lowe | 18 | A1080 | Design package 08 | Engineering | Completed | 2024-01-28 | 2024-01-31 | 100 | 2024-01-28 | 2024-01-31 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 8
Dan Lowe - Design Lead | Dan Lowe | 19 | A1090 | Design package 09 | Engineering | Completed | 2024-01-29 | 2024-02-01 | 100 | 2024-01-29 | 2024-02-01 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 9
Dan Lowe - Design Lead | Dan Lowe | 20 | A1100 | Design package 10 | Engineering | Completed | 2024-01-30 | 2024-02-03 | 100 | 2024-01-30 | 2024-02-03 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 10
Dan Lowe - Design Lead | Dan Lowe | 21 | A1110 | Design package 11 | Engineering | Completed | 2024-02-01 | 2024-02-15 | 100 | 2024-02-01 | 2024-02-15 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 11
Dan Lowe - Design Lead | Dan Lowe | 22 | A1120 | Design package 12 | Engineering | Completed | 2024-02-08 | 2024-02-11 | 100 | 2024-02-08 | 2024-02-11 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 12
Dan Lowe - Design Lead | Dan Lowe | 23 | A1130 | Design package 13 | Engineering | Completed | 2024-02-09 | 2024-02-12 | 100 | 2024-02-09 | 2024-02-12 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 13
Dan Lowe - Design Lead | Dan Lowe | 24 | A1140 | Design package 14 | Engineering | Completed | 2024-02-10 | 2024-02-17 | 100 | 2024-02-10 | 2024-02-17 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 14
Dan Lowe - Design Lead | Dan Lowe | 25 | A1150 | Design package 15 | Engineering | Completed | 2024-02-13 | 2024-02-17 | 100 | 2024-02-13 | 2024-02-17 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 15
Dan Lowe - Design Lead | Dan Lowe | 26 | A1160 | Design package 16 | Engineering | Completed | 2024-02-15 | 2024-02-29 | 100 | 2024-02-15 | 2024-02-29 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 16
Dan Lowe - Design Lead | Dan Lowe | 27 | A1170 | Design package 17 | Engineering | Completed | 2024-02-22 | 2024-03-07 | 100 | 2024-02-22 | 2024-03-07 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 17
Dan Lowe - Design Lead | Dan Lowe | 28 | A1180 | Design package 18 | Engineering | Completed | 2024-02-29 | 2024-03-03 | 100 | 2024-02-29 | 2024-03-03 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 18
Dan Lowe - Design Lead | Dan Lowe | 29 | A1190 | Design package 19 | Engineering | Completed | 2024-03-01 | 2024-03-08 | 100 | 2024-03-01 | 2024-03-08 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 19
Priya Menon - Project Manager | Priya Menon | 11 | A1000 | Design package 00 | Engineering | Completed | 2024-01-02 | 2024-01-09 | 100 | 2024-01-02 | 2024-01-09 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 20
Priya Menon - Project Manager | Priya Menon | 13 | A1590 | Build package 59 | Construction | Not Started | 2025-01-03 | 2025-01-24 | 0 |  |  |  |  | 0 | Not changed yet |  | 0 |  | 1 | 1 | 21
Sara Moss - Site Manager | Sara Moss | 11 | A1200 | Build package 20 | Construction | Completed | 2024-03-04 | 2024-03-18 | 100 | 2024-03-04 | 2024-03-18 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 22
Sara Moss - Site Manager | Sara Moss | 12 | A1220 | Build package 22 | Construction | Completed | 2024-03-18 | 2024-04-01 | 100 | 2024-03-18 | 2024-04-01 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 23
Sara Moss - Site Manager | Sara Moss | 13 | A1240 | Build package 24 | Construction | Completed | 2024-03-30 | 2024-06-08 | 100 | 2024-03-30 | 2024-06-08 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 24
Sara Moss - Site Manager | Sara Moss | 14 | A1260 | Build package 26 | Construction | Completed | 2024-05-09 | 2024-05-16 | 100 | 2024-05-09 | 2024-05-16 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 25
Sara Moss - Site Manager | Sara Moss | 15 | A1280 | Build package 28 | Construction | Completed | 2024-05-14 | 2024-06-04 | 100 | 2024-05-14 | 2024-06-04 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 26
Sara Moss - Site Manager | Sara Moss | 16 | A1300 | Build package 30 | Construction | Completed | 2024-05-25 | 2024-06-08 | 100 | 2024-05-25 | 2024-06-08 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 27
Sara Moss - Site Manager | Sara Moss | 17 | A1320 | Build package 32 | Construction | In Progress | 2024-06-04 | 2024-06-11 | 80 | 2024-06-04 |  |  |  | 0 | Finish date needed |  | 0 | Yes | 1 | 1 | 28
Sara Moss - Site Manager | Sara Moss | 18 | A1340 | Build package 34 | Construction | In Progress | 2024-06-08 | 2024-06-12 | 40 | 2024-06-08 |  |  |  | 0 | Finish date needed |  | 0 | Yes | 1 | 1 | 29
Sara Moss - Site Manager | Sara Moss | 19 | A1360 | Build package 36 | Construction | In Progress | 2024-06-15 | 2024-07-06 | 10 | 2024-06-15 |  |  |  | 0 | Not changed yet |  | 0 |  | 1 | 1 | 30
Sara Moss - Site Manager | Sara Moss | 20 | A1380 | Build package 38 | Construction | In Progress | 2024-06-28 | 2024-07-12 | 60 | 2024-06-28 |  |  |  | 0 | Not changed yet |  | 0 | Yes | 1 | 1 | 31
Sara Moss - Site Manager | Sara Moss | 21 | A1400 | Build package 40 | Construction | Not Started | 2024-08-09 | 2024-08-16 | 0 |  |  |  |  | 0 | Not changed yet |  | 0 | Yes | 1 | 1 | 32
Sara Moss - Site Manager | Sara Moss | 22 | A1420 | Build package 42 | Construction | Not Started | 2024-08-22 | 2024-08-25 | 0 |  |  |  |  | 0 | Not changed yet |  | 0 |  | 1 | 1 | 33
Sara Moss - Site Manager | Sara Moss | 23 | A1440 | Build package 44 | Construction | Not Started | 2024-09-02 | 2024-09-09 | 0 |  |  |  |  | 0 | Not changed yet |  | 0 |  | 1 | 1 | 34
Sara Moss - Site Manager | Sara Moss | 24 | A1460 | Build package 46 | Construction | Not Started | 2024-09-15 | 2024-09-18 | 0 |  |  |  |  | 0 | Not changed yet |  | 0 | Yes | 1 | 1 | 35
Sara Moss - Site Manager | Sara Moss | 25 | A1480 | Build package 48 | Construction | Not Started | 2024-09-19 | 2024-10-03 | 0 |  |  |  |  | 0 | Not changed yet |  | 0 | Yes | 1 | 1 | 36
Sara Moss - Site Manager | Sara Moss | 26 | A1500 | Build package 50 | Construction | Not Started | 2024-10-01 | 2024-10-05 | 0 |  |  |  |  | 0 | Not changed yet |  | 0 |  | 1 | 1 | 37
Sara Moss - Site Manager | Sara Moss | 27 | A1520 | Build package 52 | Construction | Not Started | 2024-10-05 | 2024-10-16 | 0 |  |  |  |  | 0 | Not changed yet |  | 0 |  | 1 | 1 | 38
Sara Moss - Site Manager | Sara Moss | 28 | A1540 | Build package 54 | Construction | Not Started | 2024-11-14 | 2024-11-17 | 0 |  |  |  |  | 0 | Not changed yet |  | 0 | Yes | 1 | 1 | 39
Sara Moss - Site Manager | Sara Moss | 29 | A1560 | Build package 56 | Construction | Not Started | 2024-11-20 | 2024-12-04 | 0 |  |  |  |  | 0 | Not changed yet |  | 0 |  | 1 | 1 | 40
Sara Moss - Site Manager | Sara Moss | 30 | A1580 | Build package 58 | Construction | Not Started | 2024-11-29 | 2025-02-07 | 0 |  |  |  |  | 0 | Not changed yet |  | 0 |  | 1 | 1 | 41
Tom Reid - Package Manager | Tom Reid | 11 | A1210 | Build package 21 | Construction | Completed | 2024-03-11 | 2024-03-25 | 100 | 2024-03-11 | 2024-03-25 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 42
Tom Reid - Package Manager | Tom Reid | 12 | A1230 | Build package 23 | Construction | Completed | 2024-03-25 | 2024-04-05 | 100 | 2024-03-25 | 2024-04-05 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 43
Tom Reid - Package Manager | Tom Reid | 13 | A1250 | Build package 25 | Construction | Completed | 2024-05-04 | 2024-05-15 | 100 | 2024-05-04 | 2024-05-15 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 44
Tom Reid - Package Manager | Tom Reid | 14 | A1270 | Build package 27 | Construction | Completed | 2024-05-12 | 2024-05-16 | 100 | 2024-05-12 | 2024-05-16 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 45
Tom Reid - Package Manager | Tom Reid | 15 | A1290 | Build package 29 | Construction | Completed | 2024-05-24 | 2024-05-27 | 100 | 2024-05-24 | 2024-05-27 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 46
Tom Reid - Package Manager | Tom Reid | 16 | A1310 | Build package 31 | Construction | Completed | 2024-06-01 | 2024-06-08 | 100 | 2024-06-01 | 2024-06-08 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 47
Tom Reid - Package Manager | Tom Reid | 17 | A1330 | Build package 33 | Construction | Completed | 2024-06-07 | 2024-06-10 | 100 | 2024-06-07 | 2024-06-10 |  |  | 0 | ✓ Complete |  | 0 |  | 1 | 1 | 48
Tom Reid - Package Manager | Tom Reid | 18 | A1350 | Build package 35 | Construction | In Progress | 2024-06-10 | 2024-06-21 | 60 | 2024-06-10 |  |  |  | 0 | Finish date needed |  | 0 | Yes | 1 | 1 | 49
Tom Reid - Package Manager | Tom Reid | 19 | A1370 | Build package 37 | Construction | In Progress | 2024-06-25 | 2024-07-02 | 40 | 2024-06-25 |  |  |  | 0 | Not changed yet |  | 0 | Yes | 1 | 1 | 50
Tom Reid - Package Manager | Tom Reid | 20 | A1390 | Build package 39 | Construction | Not Started | 2024-07-05 | 2024-09-13 | 0 |  |  |  |  | 0 | Not changed yet |  | 0 | Yes | 1 | 1 | 51
Tom Reid - Package Manager | Tom Reid | 21 | A1410 | Build package 41 | Construction | Not Started | 2024-08-12 | 2024-09-02 | 0 |  |  |  |  | 0 | Not changed yet |  | 0 | Yes | 1 | 1 | 52
Tom Reid - Package Manager | Tom Reid | 22 | A1430 | Build package 43 | Construction | Not Started | 2024-08-23 | 2024-09-13 | 0 |  |  |  |  | 0 | Not changed yet |  | 0 | Yes | 1 | 1 | 53
Tom Reid - Package Manager | Tom Reid | 23 | A1450 | Build package 45 | Construction | Not Started | 2024-09-05 | 2024-09-26 | 0 |  |  |  |  | 0 | Not changed yet |  | 0 |  | 1 | 1 | 54
Tom Reid - Package Manager | Tom Reid | 24 | A1470 | Build package 47 | Construction | Not Started | 2024-09-16 | 2024-09-23 | 0 |  |  |  |  | 0 | Not changed yet |  | 0 | Yes | 1 | 1 | 55
Tom Reid - Package Manager | Tom Reid | 25 | A1490 | Build package 49 | Construction | Not Started | 2024-09-26 | 2024-10-07 | 0 |  |  |  |  | 0 | Not changed yet |  | 0 | Yes | 1 | 1 | 56
Tom Reid - Package Manager | Tom Reid | 26 | A1510 | Build package 51 | Construction | Not Started | 2024-10-03 | 2024-10-07 | 0 |  |  |  |  | 0 | Not changed yet |  | 0 |  | 1 | 1 | 57
Tom Reid - Package Manager | Tom Reid | 27 | A1530 | Build package 53 | Construction | Not Started | 2024-10-10 | 2024-12-19 | 0 |  |  |  |  | 0 | Not changed yet |  | 0 | Yes | 1 | 1 | 58
Tom Reid - Package Manager | Tom Reid | 28 | A1550 | Build package 55 | Construction | Not Started | 2024-11-15 | 2024-11-26 | 0 |  |  |  |  | 0 | Not changed yet |  | 0 |  | 1 | 1 | 59
Tom Reid - Package Manager | Tom Reid | 29 | A1570 | Build package 57 | Construction | Not Started | 2024-11-27 | 2024-12-01 | 0 |  |  |  |  | 0 | Not changed yet |  | 0 |  | 1 | 1 | 60

## Lists (hidden)
Person | Show | Delay cause | Where things stand | Activities
Everyone | All activities | Design / information | Need attention | 3
Dan Lowe - Design Lead | Needs attention | Consents / permits | Not changed yet | 24
Priya Menon - Project Manager | Not updated yet | Access / land | Updated | 0
Sara Moss - Site Manager | Updated | Utilities / services | Complete | 33
Tom Reid - Package Manager | Finishing late | Ground conditions
| Critical, not finished | Weather
| Not started | Labour / resources
| In progress | Plant / materials
| Complete | Supplier / subcontractor
Client / instruction
Interface / other works
Other